## Slide 1: MT EDEN SW RELOCATION CURVED ALIGNMENT TUNNEL- A MORE DIRECT APPROACH
Alistair Briffett

## Slide 2
Largest infrastructure project undertaken in NZ to date
3.45km of twin tunnel underground rail
Up to 42m below the ground at its deepest point
Significant Enabling works required to facilitate this project => C6 contract
Introduction:

## Slide 3
C6 – Mt Eden Stormwater Relocation
Clash between new alignment vs Existing DN1900 Stormwater main
Necessitated 425lm of 1950mm ID tunnel to divert out of alignment
Introduction:

## Slide 4
Two drives from Central drive shaft
3 shafts in total
Upstream and Downstream connections circa 15-20m bgl
Specimen Design:

## Slide 5: Specimen Design Challenges: Geotech
Ground Conditions:
Considerably Variable
ECBF Spur
Basalt Lava flows

## Slide 6: Specimen Design Challenges: Water Street Shaft
Pros:
Over 3,000m2 of available area and already cleared so could start early
Shaft located well away from Kiwirail zone of influence
Multiple access points off both Water St and Normanby Rd
Cons:
It was designated as a reception shaft not a drive shaft
Any stored pipes had to be double handled
Distance to pump tunnel slurry if used to locate processing facility

## Slide 7: Specimen Design Challenges: Mt Eden Rd Shaft
Pros:
Not a lot…
Cons:
Required disruptive Traffic Management on busy route to facilitate deliveries of pipes and launch of MTBM
Located within 8m of live rail corridor => significant restrictions on construction activities
Very confined site with limited access
Significant temp works required to facilitate shaft and site compound

## Slide 8: Specimen Design Challenges: Nikau Street Shaft
Pros:
Approx. 1,000m2 of site made available by the demo of existing warehouse and temporary road closure.
Multiple access points – Ruru St and Nikau St
Cons:
Huia 2 high pressure water main located within 2m of shaft
High concentration of residential properties & Media works => Very sensitive to noise, vibration & dust etc
Significant seam of basalt in footprint of shaft

## Slide 9
Alternative Alignment:
Aim:
Take advantage of the natural benefits of Water St site,
Avoiding the worst of the basalt rock formation
Reduce size of Mt Eden shaft and temp works associated with it
The solution:
Single Drive from Water St
Over 90% of new alignment to be tunnelled on a curve
First curve at 150m radius
Second curve at 450m radius
VS
Alternative
Specimen

## Slide 10
Alternative Alignment Challenges:
MTBM Selection
MTBM fitted with short Steering modules to fit within the required chord of the 150m Radius curve
Second Steering module added to provide additional capacity for active steering
Fitted with hydraulic cylinders to actuated by the TBM pilot to correct any deviation
Additional 2nd Steering joint
1st Steering joint (originally integrated in the MTBM)

## Slide 11
Alternative Alignment Challenges:
Precast Pipe selection
Pipe segments needed to be short to fit the chord
Joints needed to be able to withstand the tangential thrust force while maintaining water tightness
Required a departure from NZ standards to switch to European standard detail
This would require custom build if to be manufactured in NZ => for 425lm not economically viable => Pipe had to be sourced from Malaysia
Additional QAQC checks undertaken to demonstrate compliance

## Slide 12
Alternative Alignment Challenges:
Uniform jacking force at joints
Due to curve, no full contact between pipes at joint => Unequal concentration of jacking force => Risk of failure of pipe concrete
Jackcontrol JC250 single loop hydraulic packer implemented to evenly distribute the jacking forces around the full joint
Able to be grout filled afterwards to maintain watertightness

## Slide 13
Alternative Alignment Challenges:
Cutting Head selection
Significantly variable geological units likely to be encountered during the single drive – very soft Tauranga group clays to extremely hard Basalt
Limited opportunity to make significant changes to the head during the tunnelling
Custom head constructed
Disk cutters for the basalt rock
Scrappers and sufficiently sized opening ratios to avoid the risk of clogging due to soft plastic alluvium material

## Slide 14
Alternative Alignment Challenges:
Ensuring Positional Tolerance
Ensuring positional tolerance critical
Daily traverses of the tunnel alignment undertaken by external team of Surveyors
The results used to verify the position and calibrate instrumentation in the control cabin
Benefit of this seen when the team were able to correct an understeer caused by the variable geology.

## Slide 15
Realised Benefits:
Operational Benefits
Continuity of tunnelling operation => single drive, no re-establishment of TBM
Larger drive site = > more room for storage allowed for offline preparation of pipes and cut down on double handling
Concentrated operations away from Kiwirail corridor
4 months quicker on the tunnelling than the conforming programme

## Slide 16
Realised Benefits:
Stakeholder Benefits
Less Traffic Management disruption to key arterial traffic routes
Safer site access points
Less risk to third party assets such as rail corridor
Quicker tunnelling duration

## Slide 17: Questions & Answers: